## test_admin
Test Case Project |  | Admin Access API Testing | Test Case Description
Created By |  | Samriddhi | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  | Initial unit tests written using pytest for admin access service
Tester's Name |  | Samriddhi | Date Tested | 2025-05-06 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify admin service methods return correct access control results using unit tests with mocked MySQL connection
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Test get_access_requests |  | Should return a list of access requests with expected structure | As Expected |  | Pass
2 | Test get_user_access_data |  | Should return list of users with approved access | As Expected |  | Pass
3 | Test update_request_status with valid ID |  | Should execute update query and return True | As Expected |  | Pass
Dialogue box for forgot password
4 | Test grant_access_to_user with valid request ID |  | Should update user's regions and request status, returning True | As Expected |  | Pass
5 | Test grant_access_to_user with invalid request ID |  | Should return False when no data is found | As Expected |  | Pass

## Contact
Test Case Project |  | Contact Form | Test Case Description | Validates form rendering and successful submission of contact form
Created By |  | Akshaya | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  | Review contact form with test inputs and assert confirmation message
Tester's Name |  | Akshaya | Date Tested | 2025-05-06 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Contact form should submit successfully with valid data
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Fill and submit contact form |  | "Thank you for your message!" and follow-up text appears | Same as expected |  | Pass
2
2
3

## Loc req
Test Case Project |  | LocationRequest Form Test | Test Case Description | Validates title rendering, validation errors, and successful submission
Created By |  | Akshaya | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  | Includes both validation and successful form submission
Tester's Name |  | Akshaya | Date Tested | 2025-05-06 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Form should show validation errors when empty, and submit when valid
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Submit form without filling fields |  | Shows all validation error messages | Same as expected |  | Pass
2 | Fill all fields and submit the form |  | Form submits successfully without errors | No errors, success flow triggered |  | Pass
2
3

## Login modal
Test Case Project |  | Login Modal | Test Case Description | Verifies if modal renders when open and not when closed
Created By |  | Lishita | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  | Tested modal visibility, email validation errors, and login success behavior. All expected outcomes matched actual results.
Tester's Name |  | Lishita | Date Tested | 2025-05-06 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Modal should appear only when isOpen is true
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Render modal with isOpen=true |  | Modal with heading “Login” appears | Same as expected |  | Pass
2 | Render modal with isOpen=false |  | No "Login" text should appear | Same as expected |  | Pass
3 | Invalid user email shows correct error |  | Error "User accounts must use..." appears | Same as expected |  | Pass
4 | Invalid admin email shows correct error |  | Error "Admin accounts must use..." appears | Same as expected |  | Pass
5 | Successful login triggers close (commented) |  | onCloseMock should be called | Same as expected |  | Pass

## Navbar
Test Case Project |  | Navbar | Test Case Description | To verify Login button display and click when logged out
Created By |  | Lishita | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  | Includes both validation and successful form submission
Tester's Name |  | Lishita | Date Tested | 2025-05-06 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Tested modal visibility for isOpen=true and isOpen=false; results matched expectations.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Login button shows when user not logged in |  | Login button is visible | Same as expected |  | Pass
2 | Clicking Login calls openLoginModal |  | openLoginModal function is triggered | Same as expected |  | Pass
2
3

## user
Test Case Project |  | Back-End User Service | Test Case Description |  | Validate user access retrieval and notification retrieval functionalities
Created By |  | Mahardhi | Reviewed By |  |  | Version |  | 1.0
QA Tester’s Log |  | Initial Unit Tests for User Access & Notification Services
Tester's Name |  | Mahardhi | Date Tested | 2025-05-06 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Test access-related methods from user_service module.
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 |  | Call get_accessible_locations(1) | Should return a list of locations | Returns a list |  |  | Pass
2 | Call get_notifications() |  | Should return a list of notifications | Returns a list |  |  | Pass
3 | Use test_user_data fixture to prepare request data |  | Data is returned in dict format | Fixture returns expected dict |  |  | Pass

## signup
Test Case Project |  |  | Signup Component | Test Case Description | Unit tests for validating Step 1 and navigation to Step 2
Created By |  |  | Sanjana | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  |  | Review comments in version 1.0
Tester's Name |  |  | Sanjana | Date Tested | 2025-05-06 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario |  | Ensure input validation and step navigation in Signup component works properly
Step # | Step Details |  |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Render Signup component and verify Step 1 fields |  |  | Form should display fields: role, full name, email, phone | All fields present |  | Pass
2 | Click "Next" without filling Step 1 |  |  | Error messages for required fields should be shown | Validation messages for name, email, and phone appear |  | Pass
3 | Enter valid name, email, and phone then click "Next" |  |  | Should move to Step 2 and display professional information | Step 2 heading "Professional Information" appears |  | Pass

## test_auth
Test Case Project |  | User Authentication API (Auth Service) | Test Case Description | Unit tests for create_user, login_user, and login_admin functions
Created By |  | Aditya Sahoo | Reviewed By |  | Version |  | 1.0
QA Tester’s Log |  | Review comments in version 1.0
Tester's Name |  | Aditya Sahoo | Date Tested | 2025-05-06 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify that user/admin creation and login logic work with database mocks
Step # |  |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Call create_user with valid dummy user data |  | User creation query should be executed, and connection should be closed | Query executed, commit and close called |  | Pass
2 | Call login_user with correct credentials |  | Should return user tuple from mock DB | Returned mock user tuple |  | Pass
3 | Call login_user with incorrect credentials |  | Should return None | Returned None |  | Pass
4 | Call login_admin with correct admin credentials |  | Should return admin user tuple | Returned mock admin tuple |  | Pass
5 | Call login_admin with incorrect credentials |  | Should return None | Returned None |  | Pass